## Story_Tasks_Tests
Team 2 Docs |  | Completed by: | [Oscar Bernal, Jim Esposito, Melony Henderson, Richard Robinson ]
|  | Project Deadline: | [07/22/2012]
Done? | Initial Story Card | Due By | Notes
Yes | Planning | 2012-06-19 | initial planning meetng
Yes | Preparation | 2012-06-19 | contact information exchange within the team
Yes | Get specifications from client | 2012-06-21 | get with client for project specifications
Yes | Planning/Preparation | 2012-06-21 | team meeting to plan implementation of client specs
Yes | Planning/Preparation | 2012-06-21 | get link for documentation form/update team/submit paperwork
Yes | 1st Progress Report | 2012-06-28 | present oral progress report
Yes | 2nd Progress Report | 2012-07-03 | present oral progress report
Yes | 3rd Progress Repoprt | 2012-07-12 | present oral progress report
No | Present Product | 2012-07-19 | pesent product/presentation/documentaion/paper
Done? | Customer Story Card | Due By | Notes
Yes | Planning | 2012-06-22 | meet with client to get project specifications
Yes | client | 2012-06-22 | specify deadline/expectations from client/prioritize tasks from client
Yes | 1st Progress Report | 2012-06-28 | folow-up with client/status reports
Yes | 2nd Progress Report | 2012-07-03 | folow-up with client/status reports
Yes | 3rd Progress Repoprt | 2012-07-12 | folow-up with client/status reports
No | Present Product | 2012-07-19 | pesent product/presentation/documentaion/paper
Done? | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
No | <action> | 2012-06-28
| <action> | 2012-06-28
| <action> | 2012-06-28

## Story Cards
Team 2 Story Boards |  | Completed by: | [Oscar Bernal, Jim Esposito, Melony Henderson, Richard Robinson ]
|  | Project Deadline: | [07/22/2012]
Done? | Initial Story Card | Due By | Notes
Yes | Planning | 2012-06-19 | initial planning meetng
Yes | Preparation | 2012-06-19 | contact information exchange within the team
Yes | Get specifications from client | 2012-06-21 | get with client for project specifications
Yes | Planning/Preparation | 2012-06-21 | team meeting to plan implementation of client specs
Yes | Planning/Preparation | 2012-06-21 | get link for documentation form/update team/submit paperwork
Yes | 1st Progress Report | 2012-06-28 | present oral progress report
Yes | 2nd Progress Report | 2012-07-03 | present oral progress report
Yes | 3rd Progress Repoprt | 2012-07-12 | present oral progress report
Yes | Present Product | 2012-07-19 | pesent product/presentation/documentaion/paper
Done? | Customer Story Card | Due By | Notes
Yes | Planning | 2012-06-22 | meet with client to get project specifications
Yes | client | 2012-06-22 | specify deadline/expectations from client/prioritize tasks from client
Yes | 1st Progress Report | 2012-06-28 | folow-up with client/status reports
Yes | 2nd Progress Report | 2012-07-03 | folow-up with client/status reports
Yes | 3rd Progress Repoprt | 2012-07-12 | folow-up with client/status reports
Yes | Present Product | 2012-07-19 | pesent product/presentation/documentaion/paper

## Test Cards
Team 2 Test Cards
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | click login | 2012-07-15 | request to enter user id or create an account | Pass | valid user id, login else register | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
2 | authentication-login | 2012-07-15 | enter valid user id and password | Pass | valid user password (>6 characters to include 1 letter, 1 number) | 1 | selcet reflector | 2012-06-26 | select reflector B or C | Pass | choose reflector B or C
3 | authentication-registration | 2012-07-15 | create an account | Pass | not a valid user; follow instructions to create an account and valid password (>6 characters to include 1 letter, 1 number) | 2 | select 1st rotor | 2012-06-26 | select 1sr rotor setting | Pass | choose 1st rotor setting
4 | forgot password | 2012-07-15 | select forgot password | Pass | reset password(>6 characters, 1 letter, 1 number) to be sent to e-mail address of record | 3 | select 2nd rotor | 2012-06-26 | select 2nd rotor setting | Pass | choose 2nd rotor setting
5 | valid user id | 2012-07-15 | enter valid user id and password | Pass | continue to site | 4 | select 3rd rotor | 2012-06-26 | select 3rd rotor setting | Pass | choose 3rd rotor setting
6 | invalid user id | 2012-07-15 | enter invalid us id | Pass | sned to registration screen; follow instruction to create an account and valid password (>6 characters, 1 letter, 1 number) | 5 | select plug settiings | 2012-06-26 | select plug settings | Fail | choose 13 mock plugs
7 | [5 empty] | 6 | enter plain text message | 2012-06-26 | select plain text message | Pass | choose test words "ENIGMA MACHINE"
8 | [5 empty] | 7 | trace plain text message | 2012-06-26 | trace plain text message | Fail | trace plain text test words using spread sheet rotors and relfectors/note encrypted message for return
9 | [5 empty] | 8 | trace encrypted message | 2012-06-26 | trace encrypted message | Fail | trace encrypted message using spread sheet rotors and reflectors
10 | [5 empty] | 9 | select 1st rotor w/step | 2012-06-26 | select 1st rotor setting with notch | Pass | choose 1st rotor setting at notch for step encryption
11 | [5 empty] | 10 | trace plain text message w/step | 2012-06-26 | trace plain text messagae with notch | Fail | trace plain text test words using spread sheet rotors with notch and relfectors/note encrypted message for return
12 | [5 empty] | 11 | trace encrypted message w/step | 2012-06-26 | trace encrypted message with notch | Fail | trace encrypted message using spread sheet rotors with notch and reflectors
12
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | login to account | 2012-07-17 | login screen | Pass | login with user id and password | 1 | <action> | 2012-06-28
2 | set reflector | 2012-07-17 | set reflector, 1st wheel from left | Pass | select reflector to B or C as determined by designated code | 2 | <action> | 2012-06-28
3 | set rotors | 2012-07-17 | set rotatrs, 2nd, 3rd, 4th wheels from left | Pass | select rotors as determined by designated code | 3 | <action> | 2012-06-28
4 | set plugs | 2012-07-17 | set plugs | Pass | select plugs as determned by designated code, not to exceed 10 connections, no duplicate letters | 4
5 | send plain text message | 2012-07-17 | type plain text message (ex. HELLO) | Pass | Note plain text; note encrypted text | 5
6 | send encrypted message | 2012-07-17 | type received message | Pass | enter encrypted text; note decrypted text as original message | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Test Case #: Test Cse Name: Login/Registration Page: 1 of 3
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: OSCAR BERNAL & MELONY HENDERSON Execution Date: 07/15/2012
Short Description: Test login and registration procedures; test out password/authentication.
Test Results: After several failed attempts and detailed research, authentication and login is being validated utilizing FaceBook.
Test Case #: Test Cse Name: Manual Encryption/Decryption Page:3 of 3
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Oscar Bernal & Melony Henderson Execution Date: 6/26/2012
Short Description: Manually tested enryption/decryption for rotoar and reflector flow.
Test Results: Manual testing of German Enigma Simulator Encryption/Decryption message failed. Misunderstanding of machanical workings for rotors and reflectors caused invalid results for encryption and decryption. The flow was
off and cause failure for the step method as well. Holding a RAD to get correct understanding of inner workings of machine.
Test Case #: Test Cse Name: Encryption/Decryption Page: 2 of 3
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by:Oscar Bernal, Jim Esposito, Melony Henderson, Richard Robinson Execution Date: 07/17/2012
Short Description: Test encryption/dcryption for German Enigma Simulator.
Test Results:Testing was done with the whole team using the pair program method. After a number of failed attempts and round table input, we were sucessful and thia test passed.
Test Case #: Test Cse Name: Page: of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:

## Test Cards(2)
Team 2 Test Cards
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | <action> | 2012-06-28 |  |  |  | 1 | <action> | 2012-06-28
2 | <action> | 2012-06-28 |  |  |  | 2 | <action> | 2012-06-28
3 | <action> | 2012-06-28 |  |  |  | 3 | <action> | 2012-06-28
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | <action> | 2012-06-28 |  |  |  | 1 | <action> | 2012-06-28
2 | <action> | 2012-06-28 |  |  |  | 2 | <action> | 2012-06-28
3 | <action> | 2012-06-28 |  |  |  | 3 | <action> | 2012-06-28
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Test Case #: Test Cse Name: Page: 5 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case #: Test Cse Name: Page: 7 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case #: Test Case Name: Page: 6 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case#: Test Case Name: Page: 8 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:

## Test Cards(3)
Team 2 Test Cards
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | <action> | 2012-06-28 |  |  |  | 1 | <action> | 2012-06-28
2 | <action> | 2012-06-28 |  |  |  | 2 | <action> | 2012-06-28
3 | <action> | 2012-06-28 |  |  |  | 3 | <action> | 2012-06-28
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | <action> | 2012-06-28 |  |  |  | 1 | <action> | 2012-06-28
2 | <action> | 2012-06-28 |  |  |  | 2 | <action> | 2012-06-28
3 | <action> | 2012-06-28 |  |  |  | 3 | <action> | 2012-06-28
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Test Case #: Test Cse Name: Page: 9 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description:
Test Results:
Test Case #: Test Cse Name: Page: 11 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case #: Test Case Name: Page: 10 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case#: Test Case Name: Page: 12 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:

## Test Cards(4)
Team 2 Test Cards
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | <action> | 2012-06-28 |  |  |  | 1 | <action> | 2012-06-28
2 | <action> | 2012-06-28 |  |  |  | 2 | <action> | 2012-06-28
3 | <action> | 2012-06-28 |  |  |  | 3 | <action> | 2012-06-28
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments | Steps | Test Cases | Due By | Expected Response | Pass/Fail | Notes/Comments
1 | <action> | 2012-06-28 |  |  |  | 1 | <action> | 2012-06-28
2 | <action> | 2012-06-28 |  |  |  | 2 | <action> | 2012-06-28
3 | <action> | 2012-06-28 |  |  |  | 3 | <action> | 2012-06-28
4 | [5 empty] | 4
5 | [5 empty] | 5
6 | [5 empty] | 6
7 | [5 empty] | 7
8 | [5 empty] | 8
9 | [5 empty] | 9
10 | [5 empty] | 10
11 | [5 empty] | 11
12 | [5 empty] | 12
Test Case #: Test Cse Name: Page: 13 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description:
Test Results:
Test Case #: Test Cse Name: Page: 15 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case #: Test Case Name: Page: 14 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results:
Test Case#: Test Case Name: Page: 16 of
Designed by: Melony Henderson Design Date: 6/22/2012
Executed by: Execution Date:
Short Description: Test
Test Results: